LegalEaseAI

Phase 4 — Project Planning

Backlog, sprint plan, estimation, and definition of done

| Project Information | Details |
| --- | --- |
| Project Title | LegalEaseAI — AI-Powered Legal Document Generator |
| Team ID | SWTID-2026-7680 |
| Team Size | 3 |
| Team Leader | Vigneshan P |
| Team Members | Udhaya kumar R; Vimal S |
| Prepared Date | 28/09/2026 |

# Planning Approach

The team will implement the project in short, demonstrable increments. Backend contracts and prompt behaviour are established before UI polish and export features. Each sprint ends with a runnable increment that can be reviewed without requiring production deployment.

# Definition of Done

Feature is implemented in the appropriate module.

Input validation and error handling are present.

The UI can invoke the feature or the endpoint can be tested independently.

The result is reviewed for unsafe claims and missing-information placeholders.

Documentation is updated with setup and usage instructions.

Secrets are not committed and the bundled virtual environment is excluded from source control.

# Team Responsibilities

Vigneshan P acts as team leader and coordinates architecture, integration, and final review. Udhaya kumar R focuses on user interface, interaction flow, and export experience. Vimal S focuses on backend routes, Gemini integration, validation, and testing. Responsibilities may overlap during integration and review.

| Sprint | Work Item | Owner | Points | Expected Outcome |
| --- | --- | --- | --- | --- |
| Sprint 1 | Project setup, environment, FastAPI shell, health endpoint | Vigneshan P | 5 | Backend starts and reports health |
| Sprint 1 | Streamlit layout, disclaimer, input controls | Udhaya kumar R | 6 | User can enter document details |
| Sprint 2 | DocumentRequest model and /generate route | Vimal S | 7 | Validated API contract is available |
| Sprint 2 | Gemini prompt and retry handling | Vimal S | 8 | Draft generation works with configured Gemini |
| Sprint 3 | Editable preview and session-state flow | Udhaya kumar R | 6 | Generated text can be reviewed and edited |
| Sprint 3 | TXT, DOCX, PDF and logo formatting | Udhaya kumar R | 8 | Three export formats are downloadable |
| Sprint 4 | Integration testing, safety review, README and final package | All members | 8 | Demonstrable and documented v1 |

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Missing Gemini key | High | Use clear configuration error and document .env setup |
| Gemini 429/503 errors | Medium | Retry temporary failures with exponential backoff |
| AI invents legal facts | High | Constrained prompt, [TO BE COMPLETED], professional review warning |
| CORS misconfiguration | Medium | Restrict origins before production deployment |
| Large bundled .venv | Medium | Exclude .venv from delivery and version control |